Galaxy Backbone Limited

Internal Audit Management System (IAMS)

Deployment Work Plan

Timelines & Dependencies

Prepared for: Cloud Engineering Team

Target environment: GBB Internal Cloud (GCS) / On-Premises

Document version: 1.0   |   Status: Draft

# Contents

Contents	2

1. Purpose & Scope	3

2. Prerequisites — to be provided by GBB / Cloud Team	3

3. Deployment Work Plan	4

Phase 0 — Mobilisation & Access (Days 1–2)	4

Phase 1 — Infrastructure Provisioning (Days 3–6)	4

Phase 2 — Configuration & Identity (Days 5–8, overlaps Phase 1)	4

Phase 3 — Application Deployment to Staging (Days 9–12)	4

Phase 4 — UAT, Hardening & Operations Readiness (Days 13–17)	5

Phase 5 — Production Go-Live & Stabilisation (Days 18–20)	5

4. Timeline at a Glance	6

5. Roles & Responsibilities	6

6. Assumptions, Dependencies & Risks	6

# 1. Purpose & Scope

This document sets out the work plan to deploy the Internal Audit Management System (IAMS) into Galaxy Backbone's internal cloud / on-premises environment. It lists the deployment activities in sequence, indicative timelines, the owning party for each, and the dependencies that must be satisfied before each activity can begin.

IAMS is a modular-monolith application: a single Node.js backend (Express + TypeScript) serving a REST API, a Next.js web frontend, backed by a Microsoft SQL Server database, with Redis for caching, a file store for documents/evidence, SMTP for email, and read-only integration with Microsoft Entra ID (Azure AD).

Indicative total duration: approximately 4 weeks (20 working days) from environment readiness to production go-live, assuming GBB prerequisites are available on schedule. The critical path runs through infrastructure provisioning and identity (Entra ID) configuration.

# 2. Prerequisixtes — to be provided by GBB / Cloud Team

These are external dependencies the application cannot proceed without. They should be confirmed during Phase 0; any delay here shifts the whole schedule.

| # | Prerequisite | Details required | Needed by |
| --- | --- | --- | --- |
| 1 | Compute hosts | VM(s) for the Node.js backend + Next.js frontend (Linux or Windows Server, Node.js v20+). Sizing: start 4 vCPU / 8 GB. | Phase 1 |
| 2 | SQL Server instance | Microsoft SQL Server (prod + a non-prod/staging DB). Service account, connection string, and confirmation GBB DBA owns backups. | Phase 1 |
| 3 | Redis instance | Redis endpoint for cache/session (or approval to run co-located). | Phase 1 |
| 4 | File storage | Persistent volume / share for uploaded documents & evidence (and backup of it). | Phase 1 |
| 5 | SMTP relay | Host, port, credentials, and a sender address for system email (notifications, password reset, 2FA OTP). | Phase 2 |
| 6 | Entra ID app registration | OIDC client (ID, secret, tenant, redirect URI) for SSO + a Microsoft Graph app-only permission grant (read-only) for directory sync. | Phase 2 |
| 7 | DNS & TLS | Internal hostname(s) for the app and a TLS certificate; reverse proxy (e.g. Nginx/IIS/Gateway) fronting the app. | Phase 3 |
| 8 | Network access | Outbound HTTPS to Entra ID / Microsoft Graph; inbound from GBB network to the app; app-to-DB/Redis/SMTP firewall rules. | Phase 1 |
| 9 | Secrets store | Secure place to hold environment secrets (DB password, JWT secrets, Entra secret, MFA encryption key). | Phase 2 |

# 3. Deployment Work Plan

Activities are grouped into six phases. “Depends on” references prerequisite numbers from Section 2 and/or earlier tasks.

## Phase 0 — Mobilisation & Access (Days 1–2)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| Confirm all Section 2 prerequisites and target architecture; agree environments (staging, prod). | 1 day | Cloud + Dev | — |
| Grant repository / artifact and host access to the deployment team. | 0.5 day | Cloud | — |
| Finalise the environment-variable / secrets list and naming. | 0.5 day | Dev | Prereq 9 |

## Phase 1 — Infrastructure Provisioning (Days 3–6)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| Provision compute host(s) and install Node.js v20+ runtime. | 1 day | Cloud | Prereq 1 |
| Stand up SQL Server DBs (staging + prod); create service account & schema. | 1 day | Cloud + DBA | Prereq 2 |
| Provision Redis and the persistent file-storage volume. | 1 day | Cloud | Prereq 3, 4 |
| Apply firewall / network rules (app → DB, Redis, SMTP, Graph). | 1 day | Cloud | Prereq 8 |

## Phase 2 — Configuration & Identity (Days 5–8, overlaps Phase 1)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| Register / configure Entra ID OIDC app + Graph app-only read permission. | 1–2 days | Cloud + Identity | Prereq 6 |
| Configure SMTP relay and test a send. | 0.5 day | Cloud | Prereq 5 |
| Populate environment variables / secrets for staging and prod. | 1 day | Dev + Cloud | Phase 1, Prereq 9 |
| Map Entra security groups → IAMS roles (directory mapping). | 0.5 day | Dev + Audit | Entra app ready |

## Phase 3 — Application Deployment to Staging (Days 9–12)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| Build & deploy backend; build & deploy Next.js frontend. | 1 day | Dev | Phase 1, 2 |
| Run database migrations (prisma migrate deploy) + seed roles/permissions/templates. | 0.5 day | Dev + DBA | DB ready |
| Configure reverse proxy + TLS; wire health checks (GET /health). | 1 day | Cloud | Prereq 7 |
| Enable background scheduler & verify cron jobs register and run. | 0.5 day | Dev | App running |
| Smoke test: login (local + SSO), 2FA, core audit/risk/workflow flows, email, file upload. | 1 day | Dev + QA | All above |

## Phase 4 — UAT, Hardening & Operations Readiness (Days 13–17)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| User Acceptance Testing with audit users on staging. | 2–3 days | Audit + QA | Phase 3 |
| Security review: TLS, headers, rate limits, secrets handling, RBAC. | 1 day | Cloud + Dev | Phase 3 |
| Configure DB + file-store backups and a restore test. | 1 day | Cloud + DBA | Phase 1 |
| Set up monitoring, log shipping & alerting (health, errors, queue). | 1 day | Cloud | Phase 3 |
| Document runbook (start/stop, graceful shutdown, rollback). | 0.5 day | Dev | Phase 3 |

## Phase 5 — Production Go-Live & Stabilisation (Days 18–20)

| Task | Duration | Owner | Depends on |
| --- | --- | --- | --- |
| Promote configuration & deploy to production; run prod migrations + seed. | 1 day | Cloud + Dev | Phase 4 sign-off |
| Production smoke test + SSO/Graph nightly-sync verification. | 0.5 day | Dev + QA | Prod deploy |
| Go-live: enable user access; on-call standby. | 0.5 day | All | Smoke test pass |
| Hypercare / post-go-live monitoring window. | 1 day | Dev + Cloud | Go-live |

# 4. Timeline at a Glance

Indicative schedule over four working weeks. Phases 1 and 2 overlap to compress the critical path.

| Phase | Week 1 | Week 2 | Week 3 | Week 4 |
| --- | --- | --- | --- | --- |
| 0 — Mobilisation & Access | ■■ |  |  |  |
| 1 — Infrastructure | ■■■ |  |  |  |
| 2 — Config & Identity | ■■ | ■ |  |  |
| 3 — Deploy to Staging |  | ■■■■ |  |  |
| 4 — UAT & Hardening |  |  | ■■■■■ |  |
| 5 — Go-Live & Stabilise |  |  |  | ■■■ |

# 5. Roles & Responsibilities

| Party | Responsibility |
| --- | --- |
| Cloud Engineering | Provision and operate infrastructure (compute, DB host, Redis, storage, network, TLS, backups, monitoring). |
| Development team | Build artifacts, deployment, migrations/seed, app configuration, runbook, smoke tests. |
| DBA | SQL Server instance, service accounts, migration execution support, backup/restore. |
| Identity / Security | Entra ID app registration, Graph permission grant, security review. |
| Audit / Business | UAT, role-to-group mapping decisions, go-live sign-off. |

# 6. Assumptions, Dependencies & Risks

- All Section 2 prerequisites are confirmed by the end of Phase 0; the schedule shifts day-for-day with any delay (Entra ID and SQL Server are the most common blockers).

- SQL Server is the confirmed database engine; schema migrations run via Prisma against a GBB-managed instance.

- Identity is Microsoft Entra ID via OIDC for login plus Microsoft Graph (read-only) for nightly directory sync; all external integrations are read-only.

- File storage currently uses the local/persistent-volume adapter; cloud object storage (S3/Azure Blob) is a future option, not required for go-live.

- Integration with Dynafin, IMOC, Project Plus and Shared Drive, and the predictive analytics module, are out of scope for this deployment (not yet built).

- Timelines are working days and assume no major UAT defects; a defect-fix buffer should be added if UAT raises blocking issues.

— End of document —