IAMS — Deployment Work Plan

Galaxy Backbone Limited  |  Internal Audit Management System  |  Target: GBB Internal Cloud (GCS) / On-Premises

# 1. Prerequisites (provided by GBB / Cloud Team)

| # | Prerequisite | Details required |
| --- | --- | --- |
| 1 | Compute host(s) | VM(s) for the Node.js backend and Next.js frontend. Linux or Windows Server with Node.js v20+. Suggested starting size: 4 vCPU / 8 GB RAM. |
| 2 | SQL Server instance | Microsoft SQL Server for production plus a staging/non-prod database. Service account, connection string, and confirmation that the GBB DBA owns backups and migrations. |
| 3 | Redis instance | Redis endpoint for application cache and session state, or approval to run Redis co-located on the app host. |
| 4 | File storage | Persistent volume or network share for uploaded documents and audit evidence, including its own backup. |
| 5 | SMTP relay | Mail relay host, port, credentials and a sender address for system email (notifications, password reset, 2FA one-time codes). |
| 6 | Entra ID app registration | OIDC client (client ID, secret, tenant ID, redirect URI) for SSO login, plus a Microsoft Graph app-only (read-only) permission grant for nightly directory sync. |
| 7 | DNS & TLS | Internal hostname(s) for the application and a valid TLS certificate, fronted by a reverse proxy (Nginx / IIS / API gateway). |
| 8 | Network access | Firewall rules: inbound from the GBB network to the app; outbound HTTPS to Entra ID / Microsoft Graph; app-to-DB, app-to-Redis and app-to-SMTP connectivity. |
| 9 | Legacy audit data | Source extracts (spreadsheets / legacy system exports) of historical audit, risk and user data to be migrated, with a GBB data owner to validate and sign off. |

# 2. Work Plan

| Phase | Task | Dates | Owner | Dependencies |
| --- | --- | --- | --- | --- |
| 0. Mobilisation | Confirm prerequisites & architecture; agree staging and production environments; grant deployment-team access; finalise environment-variable and secrets list. | Tue 30 Jun 2026 (1 day) | Cloud + Dev | All prerequisites confirmed available; repository and host access granted. |
| 1. Infrastructure | Provision compute host(s) and install Node.js v20+; stand up SQL Server (staging + prod) with service account and schema; provision Redis and the file-storage volume; apply firewall / network rules. | Tue 30 Jun – Wed 1 Jul 2026 (2 days) | Cloud + DBA | Compute hosts, SQL Server instance, Redis, file storage and network/firewall access must all be available before this phase can start. Runs in parallel with Mobilisation. |
| 2. Config & Identity | Register/configure Entra ID OIDC app and Graph read-only permission; configure and test SMTP; populate environment variables and secrets for both environments; map Entra security groups to IAMS roles. | Mon 6 – Tue 7 Jul 2026 (2 days) | Cloud + Identity + Dev | Infrastructure must be provisioned; Entra ID app registration and SMTP relay details must be received from GBB (received 6 Jul 2026 — this phase starts on receipt). |
| 3. Deploy to Staging | Build and deploy backend and Next.js frontend; run database migrations and seed roles/permissions/templates; configure reverse proxy + TLS and health checks (GET /health); enable the background scheduler; run smoke tests (login, SSO, 2FA, audit/risk/workflow flows, email, file upload). | Wed 8 – Fri 10 Jul 2026 (3 days) | Dev + Cloud + QA | Infrastructure and configuration/identity must be complete; the database must be reachable and the DNS hostname and TLS certificate must be in place. |
| 4. Data Migration | Extract legacy audit/risk/user data; transform to the IAMS schema using staged ETL (stage raw -> map/transform -> validate -> upsert); load into staging; reconcile against source and capture rejects in a rejects table; obtain GBB data-owner sign-off. | Mon 13 – Tue 14 Jul 2026 (2 days) | Dev + Audit (data owner) | The staging environment must be live; the legacy data extracts and a GBB data owner to validate them must be available. |
| 5. Initial UAT (Round 1) & Feedback | Run the first round of User Acceptance Testing with a subset of audit users on staging, covering core audit/risk/workflow functionality; capture feedback, defects and change requests in a shared log. | Wed 15 – Thu 16 Jul 2026 (2 days) | Audit + QA | Staging must be live with migrated data validated (Phase 4 complete). |
| 6. UAT Feedback Implementation | Triage the Round 1 UAT feedback log; implement agreed fixes and change requests; regression-test the affected flows on staging. | Fri 17 Jul 2026 (1 day) | Dev + QA | Round 1 UAT feedback log must be complete and triaged with GBB sign-off on scope. |
| 7. Integration Discovery | GBB provides API documentation for IMOC, Dynafin, Active Directory, Project Plus and Shared Drive; joint working session with GBB IT/system owners to understand how data from those systems is used in the audit lifecycle (all integrations remain read-only). | Mon 20 Jul 2026 (1 day) | Dev + GBB | GBB to provide API documentation and nominate SMEs for IMOC, Dynafin, AD, Project Plus and Shared Drive walkthroughs. |
| 8. Integration Build | Build and configure the read-only adapters for IMOC, Dynafin, AD (Graph sync), Project Plus and Shared Drive per the documentation and data-flow understanding gathered in Phase 7; unit/integration test each adapter. | Tue 21 – Thu 23 Jul 2026 (3 days) | Dev + GBB | API documentation and data-flow understanding from Phase 7 must be available. |
| 9. Full UAT, Hardening & Security Review | Run a second, full round of User Acceptance Testing covering audit/risk/workflow plus the new integrations; security review (TLS, headers, rate limits, RBAC, secrets); configure DB and file-store backups with a restore test; set up monitoring, log shipping and alerting; write the operations runbook (start/stop, shutdown, rollback). | Fri 24, Mon 27 – Tue 28 Jul 2026 (3 days) | Audit + QA + Cloud + Dev | Integrations must be built and unit-tested; UAT fixes from Phase 6 must be deployed to staging. |
| 10. Training & Handover | Train audit users and system administrators on staging using migrated data and live integrations; deliver user and administrator guides; walk the cloud/ops team through the runbook (start/stop, monitoring, backups, rollback). | Wed 29 – Thu 30 Jul 2026 (2 days) | Dev + Audit + Cloud | Full UAT (Round 2) must be signed off. |
| 11. Go-Live & Stabilise | Promote configuration and deploy to production; run production migrations, seed and final data load; production smoke test plus SSO, nightly directory-sync and integration verification; enable user access; hypercare monitoring window with on-call standby. | Fri 31 Jul – Mon 3 Aug 2026 (2 days) | All | Training complete; UAT signed off; migrated data and integrations validated on staging before production go-live. |

# 3. Timeline (30 Jun 2026 – 3 Aug 2026; approx. 21 working days from GBB config handover on 6 Jul 2026)

| Phase | Start Date | End Date | Working Days |
| --- | --- | --- | --- |
| 0. Mobilisation | Tue 30 Jun 2026 | Tue 30 Jun 2026 | 1 |
| 1. Infrastructure | Tue 30 Jun 2026 | Wed 1 Jul 2026 | 2 |
| 2. Config & Identity | Mon 6 Jul 2026 | Tue 7 Jul 2026 | 2 |
| 3. Deploy to Staging | Wed 8 Jul 2026 | Fri 10 Jul 2026 | 3 |
| 4. Data Migration | Mon 13 Jul 2026 | Tue 14 Jul 2026 | 2 |
| 5. Initial UAT (Round 1) & Feedback | Wed 15 Jul 2026 | Thu 16 Jul 2026 | 2 |
| 6. UAT Feedback Implementation | Fri 17 Jul 2026 | Fri 17 Jul 2026 | 1 |
| 7. Integration Discovery | Mon 20 Jul 2026 | Mon 20 Jul 2026 | 1 |
| 8. Integration Build | Tue 21 Jul 2026 | Thu 23 Jul 2026 | 3 |
| 9. Full UAT, Hardening & Security Review | Fri 24 Jul 2026 | Tue 28 Jul 2026 | 3 |
| 10. Training & Handover | Wed 29 Jul 2026 | Thu 30 Jul 2026 | 2 |
| 11. Go-Live & Stabilise | Fri 31 Jul 2026 | Mon 3 Aug 2026 | 2 |